Table 1 - Compliance Analysis

| Clause | Requirement | Status | Evidence | Assessor Remarks | Historical Action Taken |
| --- | --- | --- | --- | --- | --- |
| Payment Terms | 45% Minimum Advance | Met | Section 4.1 enforces a clean, un-tranched forty-five percent (45%) advance payment triggered automatically upon initial engineering drawing freeze. | Avoids milestone fragmentation and ensures early cash injections are directed entirely toward long-lead casting procurement. | Negotiated milestone-based payment schedule and removed conditional payment dependencies. |
| Payment Terms | All payments Net 30 days from invoice | Met | Clause 4.4 confirms that progress payments for completed metallurgical tests shall be cleared within thirty (30) days from formal electronic invoice receipt. | Aligns cleanly with corporate baseline guidelines, removing conditional event dependencies from standard billing cycles. | Negotiated milestone-based payment schedule and removed conditional payment dependencies. |
| Payment Terms | Partial delivery and invoicing allowed | Partially Met | Supplier may split component shipments across three distinct phases, but standalone invoicing is barred until an independent inspector signs off on the total system heat-treatment logs. | The partial physical delivery parameter is met, but tying invoicing to a combined technical quality record delays milestone revenue clearance. | Negotiated milestone-based payment schedule and removed conditional payment dependencies. |
| Bank Guarantees | Performance Guarantee not exceeding 10% | Partially Met | Clause 6.1 enforces a primary 10% performance bond, but adds a rider requiring an extra 1.5% technical defect retention if factory validation data falls short of benchmarks. | The primary guarantee matches standard caps, but the conditional retention rider pushes potential aggregate security to 11.5%. | Reduced performance security from 12% to 10% through contract amendment. |
| Bank Guarantees | Bank Guarantee validity period defined | Met | All issued performance securities are valid through the exact duration of factory fabrication up to the execution of the final site acceptance protocol. | Provides an explicit, well-defined lifecycle boundary that protects corporate capital from open-ended claim windows. | Reduced performance security from 12% to 10% through contract amendment. |
| Liquidated Damages | Documentation LD not applicable | Met | Article 8.1 explicitly isolates delay penalties to physical equipment milestones, stating that late drawing or manual revisions shall not accrue liquidated damages. | Fully compliant with risk policies, keeping clerical and administrative milestones insulated from financial penalty engines. | Negotiated lower LD cap and clarified applicability conditions. |
| Liquidated Damages | Equipment Delivery LD 0.5% per week | Met | Schedule overruns regarding core modular structures incur a penalty rate fixed at exactly zero point five percent (0.5%) per completed calendar week. | Satisfies baseline commercial requirements, offering an equitable and industry-standard delay recovery framework. | Negotiated lower LD cap and clarified applicability conditions. |
| Liquidated Damages | Equipment Delivery LD capped at 5% | Met | Section 8.3 limiters restrict localized assembly delay assessments to a maximum ceiling of five percent (5.0%) of that specific delayed sub-assembly. | Effectively insulates the contractor from compounding damage claims on minor delayed peripheral components. | Negotiated lower LD cap and clarified applicability conditions. |
| Liquidated Damages | Aggregate LD capped at 5% PO value | Not Met | Clause 8.4 mandates that the absolute maximum cap for all combined delivery, testing, and schedule delays shall equal seven point five percent (7.5%) of total PO value. | Over-exposure of 2.5% beyond the mandatory corporate 5% maximum aggregate ceiling, inflating total financial risk. | Negotiated lower LD cap and clarified applicability conditions. |
| Liquidated Damages | Remedial Work LD not applicable | Partially Met | Liquidated damages do not accumulate during technical rework, provided that the modification is performed inside the primary manufacturing facility. | The exemption applies to factory errors but fails to protect the contractor if remedial or tuning work must be executed post-delivery at the project site. | Negotiated lower LD cap and clarified applicability conditions. |
| Guarantee | Warranty period defined | Met | Section 9.1 outlines an all-inclusive equipment technical guarantee framework extending across twenty-four (24) months from plant field operational integration. | Provides an exceptional, long-term operational protection runway that satisfies internal mechanical asset management rules. | Renegotiated warranty duration and coverage limits during legal review. |
| Guarantee | 2 months from commissioning or 18 months from dispatch | Partially Met | The contract defines a standard 2-month post-commissioning rule, but inserts an automatic "Deemed Validation" trigger if the buyer's upstream pipelines fail to provide feedstock within 30 days. | Shorter than ideal industry protections; shifts the financial burden of early field failures onto plant teams if utility lines delay mechanical integration. | Renegotiated warranty duration and coverage limits during legal review. |
| Guarantee | Repair/replacement warranty obligations defined | Partially Met | Swapped components receive a fresh 12-month extension, but this remedial coverage is capped by the absolute calendar expiration of the main agreement. | Severely restricts late-stage protection; repaired assets lose all coverage if a major breakdown is rectified near the end of the global warranty window. | Renegotiated warranty duration and coverage limits during legal review. |
| Force Majeure | Force majeure events defined | Partially Met | Force Majeure parameters incorporate standard environmental and labor disruptions but explicitly exclude regional power grid allocations or local fuel rationing. | The core definition is valid, but the exclusion of energy infrastructure failures creates exposure during regional power grid instability. | Expanded force majeure coverage and simplified notice requirements. |
| Force Majeure | Applies to subcontractors | Met | Excusable schedule relief protections explicitly apply to all vetted sub-contractors, foundries, and raw material logistics providers listed in the agreement. | Highly compliant positioning that prevents the main contractor from absorbing severe financial damage penalties due to upstream supplier disasters. | Expanded force majeure coverage and simplified notice requirements. |
| Force Majeure | Notice obligations defined | Partially Met | Formal written notification must be transmitted via registered mail within seventy-two (72) hours of event inception, backed by national agency confirmation. | The timeline is fair, but mandating physical registered mail during a major regional crisis or severe infrastructure collapse is impractical. | Expanded force majeure coverage and simplified notice requirements. |
| Termination | Termination rights defined | Met | Comprehensive, balanced default and commercial termination workflows are clearly articulated across the entirety of Article 11. | Provides clean alignment with organizational corporate governance models and legal risk baselines. | Revised cancellation fee structure during commercial negotiations. |
| Termination | Cancellation fee structure defined | Met | Article 11.3 details an itemized milestone percentage tracking framework that aligns cancellation charges directly with verified engineering progress stages. | Prevents arbitrary, unhedged overhead losses by guaranteeing structured cost recovery throughout the project lifecycle. | Revised cancellation fee structure during commercial negotiations. |
| Termination | 61-90 day cancellation fee 40% | Not Met | The agreement maps the convenience termination compensation charge during the 61-90 day engineering window at exactly thirty-eight percent (38.0%). | Fails to hit our corporate mandatory 40% threshold, leaving a 2% funding gap for uncompensated staging labor and raw metal designs. | Revised cancellation fee structure during commercial negotiations. |
| Suspension | Maximum 2 suspensions and 30 days aggregate | Partially Met | Suspions are capped at two iterations, but text notes that any delay in securing third-party regulatory environmental permits automatically pauses tracking limits. | The convenience limit matches parameters, but the regulatory variance allows the customer to extend project suspensions indefinitely without paying delay fees. | Added suspension approval workflow and duration limits. |
| Suspension | Supplier obligations during suspension defined | Met | The contract explicitly mandates precise nitrogen-purging protocols, environmental shielding, and routine climate-controlled maintenance for all idled components. | Secures asset integrity and establishes an auditable cost-tracking foundation for specialized field preservation labor. | Added suspension approval workflow and duration limits. |
| Change Orders | Formal amendment process defined | Met | Article 15 establishes a strict change request workflow, explicitly ranking signed amendments above preliminary engineering email logs. | Thoroughly satisfies corporate governance compliance, protecting the technical configuration from unapproved field design creep. | Implemented formal change request and approval process. |
| Change Orders | Timeline for approval defined | Met | Variations and engineering adjustments must be formally accepted or rejected by the buyer's quality board within fourteen (14) business days of submittal. | Provides strong protection against continuous, uncompensated project delays while design modifications are actively evaluated. | Implemented formal change request and approval process. |
| Governing Law | Applicable law specified | Partially Met | The purchase order identifies Indian substantive law but specifies that local state industrial codes shall supersede standard civil contract principles in conflicts. | Introduces localized legal complexity, which increases arbitration risk during cross-border enforcement scenarios. | Standardized governing law language across contracts. |
| Dispute Resolution | Arbitration mechanism defined | Met | Establishes a multi-tier dispute protocol routing all technical material disagreements through independent expert evaluation before triggering formal tribunals. | Efficiently filters out minor engineering design or radiography arguments without pausing the broader project schedule. | Updated arbitration mechanism based on prior legal review. |
| Dispute Resolution | Seat of arbitration specified | Met | The agreement names Singapore as the formal legal seat for all international arbitration proceedings, conducted under SIAC regulations. | Neutral, internationally recognized seat selection aligns perfectly with standard corporate risk management guidelines. | Updated arbitration mechanism based on prior legal review. |
| Insurance | Insurance responsibilities defined | Met | Comprehensive, all-inclusive insurance allocations—encompassing erection-all-risk, commercial general liability, and transit policies—are detailed across Article 13. | Safely insulates the business from catastrophic property loss liabilities throughout international maritime and overland transit segments. | Expanded insurance coverage obligations. |
| Insurance | Equipment damage covered while at buyer premises | Met | Clause 13.5 explicitly states that storage costs or field damage claims are without prejudice to the supplier's right to claim full insurance recovery for site errors. | Eliminates field liability for high-value components once they enter geographic areas managed exclusively by the buyer. | Expanded insurance coverage obligations. |
| Liability | Aggregate liability cap defined | Met | Section 10.1 establishes a firm, absolute aggregate liability ceiling fixed at exactly ten percent (10%) of the applicable Purchase Order value. | Perfectly aligns with internal corporate risk-tolerance thresholds for strategic heavy manufacturing agreements. | Reduced liability exposure through revised cap language. |
| Liability | Liability carve-outs defined | Partially Met | The 10% financial liability cap does not apply to the direct costs of emergency extraction or structural re-stabilization during immediate site safety shutdowns. | Excludes non-emergency or standard mechanical defects from the cap safety net, exposing the business to expanded damage claims for basic manufacturing errors. | Reduced liability exposure through revised cap language. |
| Consequential Damages | Consequential damages excluded | Partially Met | The contract contains a comprehensive mutual waiver excluding loss of revenue, profit, production, and opportunity from standard breach claims. | The baseline exclusion framework is present, but its real-world legal effectiveness is weakened by exceptions added in trailing paragraphs. | Clarified exclusions and carve-outs after legal review. |
| Consequential Damages | Exceptions to exclusion defined | Partially Met | The general waiver of consequential or indirect damages does not apply to breaches of confidentiality, third-party patent claims, or incidents of gross negligence. | Carve-outs introduce significant exposure, as standard design miscalculations can easily be reframed as gross negligence in local courts to bypass the waiver. | Clarified exclusions and carve-outs after legal review. |
| Critical Sub-Suppliers | Approved critical vendors identified | Met | Annex D names pre-cleared, high-grade forging companies and certified metallurgical foundries for all structural pressure-vessel components. | Protects structural safety metrics by ensuring all primary raw inputs originate from audited, top-tier industrial operations. | Approved alternate vendors and defined substitution controls. |
| Critical Sub-Suppliers | Vendor substitution restrictions defined | Met | Any alteration, replacement, or modification of listed sub-vendors requires express, written prior authorization from the Buyer's Quality Assurance Director. | Prevents unauthorized material substitutions by subcontractors, securing long-term asset structural reliability. | Approved alternate vendors and defined substitution controls. |

Table 2 - Risk Assessment

| Clause | Requirement | RAG | Risk | Rationale | Mitigation |
| --- | --- | --- | --- | --- | --- |
| Payment Terms | 45% Minimum Advance | Green | Balanced upstream project funding | Securing an immediate 45% cash injection eliminates negative cash curves, ensuring raw steel procurement occurs without financial delay. | Maintain the current single lump-sum payment timeline without allowing future adjustments or tranches. |
| Payment Terms | All payments Net 30 days from invoice | Green | Stable predictable billing cycles | Standard Net 30 timeframes provide healthy, reliable working capital streams to support continuous shop floor operations. | Align all payment triggers to Net 30 days from receipt of valid invoice and remove conditional acceptance prerequisites. |
| Payment Terms | Partial delivery and invoicing allowed | Amber | Milestone billing stagnation and extended working capital lockups | Restricting progress invoicing until an independent inspector signs off on combined heat logs prevents regular progress billing for completed components. | Revise the language to permit independent, proportional invoicing immediately upon the completion and dispatch of each individual lot. |
| Bank Guarantees | Performance Guarantee not exceeding 10% | Amber | Extended financial security requirements and credit line friction | Allowing conditional retention riders to expand total performance bonds to 11.5% locks up corporate credit lines and inflates bank fee overheads. | Reduce total performance security to a maximum of 10 percent including bridge guarantees. |
| Bank Guarantees | Bank Guarantee validity period defined | Green | Secure, bounded performance bond lifecycles | Firm validation-event boundaries prevent clients from keeping performance guarantees open-ended, allowing smooth credit roll-offs. | Reduce total performance security to a maximum of 10 percent including bridge guarantees. |
| Liquidated Damages | Documentation LD not applicable | Green | Zero exposure for administrative delays | Explicitly protecting drawing and documentation milestones from financial penalties keeps minor revision delays from draining project profitability. | Establish a separate liquidated damages regime for documentation delays independent of equipment delivery to ensure targeted recovery for documentation failures. |
| Liquidated Damages | Equipment Delivery LD 0.5% per week | Green | Standard predictable delay penalty tracking | Standardized 0.5% weekly rates provide an equitable, balanced commercial framework for tracking late-stage engineering schedule delays. | Remove the 5% cap on individual undelivered parts and increase the aggregate delivery LD cap to 10% of the total Purchase Order value. |
| Liquidated Damages | Equipment Delivery LD capped at 5% | Green | Secure item-level damage containment | Component-specific 5% caps protect individual sub-assemblies from accumulating compounding delay liabilities that destroy specific unit margins. | Reduce aggregate delay exposure, including delivery LD and service credits, to a maximum of 5 percent of total PO value. |
| Liquidated Damages | Aggregate LD capped at 5% PO value | Red | Financial liability over-exposure | Accepting an aggregate delay penalty ceiling of 7.5% violates our mandatory 5% corporate limit, increasing total risk by 2.5%. | Reduce aggregate LD and service-credit exposure to a maximum of 5 percent of total Purchase Order value. |
| Liquidated Damages | Remedial Work LD not applicable | Amber | Compounding penalties during post-delivery field modifications | Confining rework exemptions strictly to primary factories means delay penalties continue to accrue if engineering modifications must be executed at the site. | State that liquidated damages shall not apply to remedial work, warranty repair, or replacement without conditions or limitations. |
| Guarantee | Warranty period defined | Green | Exceptional long-term protection coverage | A clean, comprehensive 24-month operational warranty shifts the financial burden of early asset defects entirely onto the supplier. | Extend standard guarantee to twelve months post-commissioning and ensure remedial guarantees extend for twelve months from repair regardless of original dispatch date. |
| Guarantee | 2 months from commissioning or 18 months from dispatch | Amber | Premature warranty expiration due to client-side utility delays | Brief 2-month post-commissioning limits combined with 30-day "Deemed Validation" clauses risk expiring product protection before the plant is operational. | Extend standard guarantee to twelve months from commissioning and remove the deemed commissioning trigger for Buyer delays. |
| Guarantee | Repair/replacement warranty obligations defined | Amber | Warranty coverage gaps for late-replaced assets | Forcing remedial component warranties to expire on the primary contract date leaves late-replaced assets with zero operational protection. | Ensure repaired or replaced components are guaranteed for 12 months from completion of repair without a cap tied to original dispatch date. |
| Force Majeure | Force majeure events defined | Amber | Unexcusable schedule delays during power infrastructure failures | Excluding utility grid allocations or fuel rationing from force majeure parameters means the contractor absorbs all delay penalties if energy grids collapse. | Extend force majeure relief to all approved sub-suppliers and logistics providers regardless of whether they are specifically named in Annex D. |
| Force Majeure | Applies to subcontractors | Green | Watertight schedule insulation across sub-tier networks | Extending force majeure relief down to vetted subcontractors ensures localized raw material disasters upstream do not trigger immediate default claims. | Extend force majeure relief to all subcontractors and vendors regardless of Tier status or inclusion in Annex D. |
| Force Majeure | Notice obligations defined | Amber | Technical forfeiture of relief rights due to rigid notification channels | Mandating physical registered mail during a major regional emergency or communication collapse creates high risk of missing the 72-hour window. | Extend Force Majeure relief to all critical sub-contractors and vendors regardless of their listing in Annex D. |
| Termination | 61-90 day cancellation fee 40% | Red | Capital recovery shortfall during active engineering phases | Utilizing a 38% recovery rate during the critical mid-stage window introduces a 2% funding gap for uncompensated staging and design labor. | Increase the convenience cancellation fee for the 61-90 day window to 40% of the order value. |
| Suspension | Maximum 2 suspensions and 30 days aggregate | Amber | Extended non-compensable project delays via permitting loopholes | Allowing environmental permit delays to pause suspension tracking lets the buyer stall project execution indefinitely without change-order coverage. | Include regulatory, government, legal, and safety stoppages within the maximum two suspension and thirty day aggregate limit. |
| Governing Law | Applicable law specified | Amber | Legal cost inflation due to complex regional code overlays | Allowing local state industrial codes to supersede contract law principles introduces legal complexity and unpredictability during litigation. | Align governing law and arbitration seat to a single jurisdiction and consolidate all dispute resolution proceedings into one forum. |
| Liability | Liability carve-outs defined | Amber | Uncapped financial exposure for non-emergency technical mistakes | Confining liability cap exclusions strictly to safety shutdowns leaves the business exposed to uncapped direct damage claims for standard engineering errors. | Expand liability carve-outs to include all direct damages resulting from defective design, material, or workmanship regardless of safety shutdown status. |
| Consequential Damages | Consequential damages excluded | Amber | Potential exposure to indirect losses through trailing clause exclusions | Structuring broad exceptions within trailing sub-clauses dilutes the primary waiver, creating financial exposure for indirect business losses. | Remove the exceptions in Article 00511.15.2 to ensure a comprehensive and unconditional waiver of all consequential, indirect, and special damages for both parties. |
| Consequential Damages | Exceptions to exclusion defined | Amber | Exposure to uncapped indirect claims via gross negligence loopholes | Excluding gross negligence from the waiver creates vulnerability, as basic technical calculation errors can easily be reframed as negligence in local courts. | Narrow exceptions to the consequential damages waiver and implement an overall aggregate liability cap that applies regardless of the exception triggered. |

Table 3 - Mitigation Strategy Table

| Clause | Risk | Mitigation Recommendation |
| --- | --- | --- |
| Payment Terms | 45% Minimum Advance | Maintain the current single lump-sum payment timeline without allowing future adjustments or tranches. |
| Payment Terms | All payments Net 30 days from invoice | Align all payment triggers to Net 30 days from receipt of valid invoice and remove conditional acceptance prerequisites. |
| Payment Terms | Partial delivery and invoicing allowed | Revise the language to permit independent, proportional invoicing immediately upon the completion and dispatch of each individual lot. |
| Bank Guarantees | Performance Guarantee not exceeding 10% | Reduce total performance security to a maximum of 10 percent including bridge guarantees. |
| Bank Guarantees | Bank Guarantee validity period defined | Reduce total performance security to a maximum of 10 percent including bridge guarantees. |
| Liquidated Damages | Documentation LD not applicable | Establish a separate liquidated damages regime for documentation delays independent of equipment delivery to ensure targeted recovery for documentation failures. |
| Liquidated Damages | Equipment Delivery LD 0.5% per week | Remove the 5% cap on individual undelivered parts and increase the aggregate delivery LD cap to 10% of the total Purchase Order value. |
| Liquidated Damages | Equipment Delivery LD capped at 5% | Reduce aggregate delay exposure, including delivery LD and service credits, to a maximum of 5 percent of total PO value. |
| Liquidated Damages | Aggregate LD capped at 5% PO value | Reduce aggregate LD and service-credit exposure to a maximum of 5 percent of total Purchase Order value. |
| Liquidated Damages | Remedial Work LD not applicable | State that liquidated damages shall not apply to remedial work, warranty repair, or replacement without conditions or limitations. |
| Guarantee | Warranty period defined | Extend standard guarantee to twelve months post-commissioning and ensure remedial guarantees extend for twelve months from repair regardless of original dispatch date. |
| Guarantee | 2 months from commissioning or 18 months from dispatch | Extend standard guarantee to twelve months from commissioning and remove the deemed commissioning trigger for Buyer delays. |
| Guarantee | Repair/replacement warranty obligations defined | Ensure repaired or replaced components are guaranteed for 12 months from completion of repair without a cap tied to original dispatch date. |
| Force Majeure | Force majeure events defined | Extend force majeure relief to all approved sub-suppliers and logistics providers regardless of whether they are specifically named in Annex D. |
| Force Majeure | Applies to subcontractors | Extend force majeure relief to all subcontractors and vendors regardless of Tier status or inclusion in Annex D. |
| Force Majeure | Notice obligations defined | Extend Force Majeure relief to all critical sub-contractors and vendors regardless of their listing in Annex D. |
| Termination | 61-90 day cancellation fee 40% | Increase the convenience cancellation fee for the 61-90 day window to 40% of the order value. |
| Suspension | Maximum 2 suspensions and 30 days aggregate | Include regulatory, government, legal, and safety stoppages within the maximum two suspension and thirty day aggregate limit. |
| Governing Law | Applicable law specified | Align governing law and arbitration seat to a single jurisdiction and consolidate all dispute resolution proceedings into one forum. |
| Liability | Liability carve-outs defined | Expand liability carve-outs to include all direct damages resulting from defective design, material, or workmanship regardless of safety shutdown status. |
| Consequential Damages | Consequential damages excluded | Remove the exceptions in Article 00511.15.2 to ensure a comprehensive and unconditional waiver of all consequential, indirect, and special damages for both parties. |
| Consequential Damages | Exceptions to exclusion defined | Narrow exceptions to the consequential damages waiver and implement an overall aggregate liability cap that applies regardless of the exception triggered. |

Historical Actions Table

| Clause | Requirement | Previous Status | Action Taken | Action Owner | Review Date | Resolution Status | Reviewer Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Payment Terms | Partial delivery and invoicing allowed | Partially Met | Tied milestone billing to independent inspector sign-off on combined heat logs under CAPA-2025-077. | Quality Director | 09-Sep-2025 | Monitoring required | Added quality checks protect mechanical integrity but create administrative delays for revenue clearance. |
| Bank Guarantees | Performance Guarantee not exceeding 10% | Red | Incorporated a conditional 1.5% technical defect retention rider following factory audit non-compliance. | Engineering Lead | 14-Nov-2025 | Escalated to Procurement/Legal | Supplier rejected the retention rider; clause remains deadlocked pending global commercial alignment. |
| Liquidated Damages | Aggregate LD capped at 5% PO value | Not Met | Clause rewritten during Contract Review CR-2025-091 to apply a 7.5% aggregate ceiling on delay damages. | Corporate Counsel | 18-Jan-2026 | Risk accepted by Management | Absolute ceiling is higher than our corporate target, but risk was accepted to secure exclusive vendor access. |
| Liquidated Damages | Remedial Work LD not applicable | Amber | Imlplemented text restricting penalty exemptions strictly to work executed inside primary fabrication facilities. | Operations VP | 22-May-2025 | Clause renegotiated | Closes exposure for factory rework, but post-delivery field tuning at the site remains subject to penalty tracking. |
| Guarantee | 2 months from commissioning or 18 months from dispatch | Amber | Inserted a 30-day "Deemed Validation" clause to trigger the warranty if client pipelines delay project startup. | Commercial Mgr | 15-Jan-2025 | Vendor submitted revised wording | Modification protects the supplier from open-ended field storage liabilities caused by customer infrastructure delays. |
| Guarantee | Repair/replacement warranty obligations defined | Not Met | Refused component warranty extensions past the global contract expiration date during legal reviews. | Legal Counsel | 04-Mar-2025 | Closed after Amendment | Signed off under special clearance register; late-stage component swaps will hold zero extended protection. |
| Force Majeure | Notice obligations defined | Partially Met | Increased the notification transmission window to 72 hours but retained physical registered mail mandates. | Risk Committee | 11-May-2025 | Pending Customer Approval | Awaiting formal customer counter-signature on electronic notification backup alternatives for disaster windows. |
| Termination | 61-90 day cancellation fee 40% | Not Met | Graded termination fee table introduced in Revision 3, assigning a 38% cost recovery fee to the mid-phase window. | Commercial VP | 03-Feb-2026 | Requirement fixed after Legal Review | Closes major gaps, though it falls 2% short of our optimal corporate asset overhead recovery projection. |
| Suspension | Maximum 2 suspensions and 30 days aggregate | Partially Met | Environmental permitting delays were explicitly carved out from the 30-day aggregate suspension limit. | Internal Audit | 14-May-2024 | Monitoring required | Operational cost impacts from extended site permitting pauses will be evaluated during quarterly project reviews. |
| Liability | Liability carve-outs defined | Amber | Narrowed exclusions to safety shutdowns, ensuring standard design flaws remain inside the 10% cap protection. | Chief Counsel | 17-Dec-2025 | Requirement fixed after Legal Review | Restricts general damage exposure effectively, successfully shielding the balance sheet from standard field errors. |